## Hypothecated Funding
1. Initiaitve / Sub Intiative: As demonstrated in the current table below please state the intiative/sub initiative the deliverable is linked to.
2. Deliverable: Please outline in detail what is being delivered being specific about what it is that you will be doing to achieve the goal.
3. Related IT Investment: If a deliverable is linked to an IT Investment please list what investments and explain how it links to the deliverable.
4. Year Milestones: Please outline the key milestones you expect to reach in the respective year. These should be detailed and clear enough that it will be
obvious whether or not these milestones were met. There should be at least one milestone in each year unless the project is not expected to be started
at this point. Where this is the case please state it. Please try to avoid making dates open ended.
5.Year Success: Please detail what success would look like for each deliverable in each given year. This should be detailed and clear enough that it will be
obvious whether or not these milestones were met. – Not necessarily the specifications of what will be delivered but what will be achieved.
6. Expected final delivery date and what success looks like: Please outline when the final project will be delivered and explain what success looks like for
the final delivery of the deliverable.
Initiative D1 - End of life assets | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments for SONI to develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative | [13 empty] | SONI needs to set out milestones for all deliverables for this initiative
Desktop Infrastructure Refresh | Refresh all PCs, laptops and printers | [11 empty] | All PCs, laptops and printers refreshed |  | SONI business plan, D-35
VMware & Citrix Software Upgrades | Refresh Vmware & Citrix software | [11 empty] | Vmware & Citrix software refreshed |  | SONI business plan, D-35
Operating Systems Upgrade | Upgrade to window server 2016 | [11 empty] | Operating systems have been upgraded to window server by 2024 |  | SONI business plan, D-36
Oracle Audit Vault Refresh | Refresh oracle audit vault product | [11 empty] | Oracle audit vault refreshed |  | SONI business plan, D36
Data Centre Access Layer Switching Upgrade | Replace all data centre switches in the SPC20 period | [11 empty] | All data centre layer switches replaced with upgrades |  | SONI business plan, D37
Floor Access Layer Switching Upgrade | Replace all floor access layer switches | [11 empty] | All floor access layer switches replaced with upgrades |  | SONI business plan, D37
Wireless Infrastructure Upgrade | Replace wireless infrastructure | [11 empty] | Wireless infrastructure upgraded |  | SONI business plan, D38
Oracle Database Hardware Refresh | Refresh oracle database hardware | [11 empty] | Oracle database hardware refreshed |  | SONI business plan, D39
Dynamics On-premise Upgrade | Upgrade Dynamics on-premise solution | [11 empty] | Dynamics on-premise upgraded by 2021 |  | SONI business plan, D40
Standing Data Workbook | Implement Standing Data Workbook | [11 empty] | DSW implemented by 2024 |  | SONI business plan, D40
Private Communications Network | Implement PCN | [11 empty] | PCN solution implemented |  | SONI business plan, D41
EMS Renewal | Renew EMS | Link to TSO DSO interface capex, under renewables strategy initiative | [10 empty] | EMS renewed by 2023 to support the existing service level for EMS (99.95%) availability on annual basis and will ensure the continued delivery of 3 critical services: • Real-Time SCADA & Communications • Real-Time Situational Awareness • Dispatch of Windfarms The renewal will include but not be limited to: Critical components have been replaced Obsolete hardware has been replaced Appropriate support arrangements have been maintained with vendors Major upgrade of the EMS' underlying hardware has been completed OEM requirements are met via the upgrade of software and hardware on a defined cycle and appropriate support arrangement are maintained for mission-critical systems |  | SONI business plan, D41 SONI Deep Dive response, P1, P4
Initiative D2 – Transition to Cloud | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Server re-location | Relocation of servers that will not be moved to co-located data centres to cloud service providers (Infrastructure as a Service) | [11 empty] | SONI have improved costs through operational server maintenance, savings in the region of £15m over the remaining life span (5 years). Approx. £1 5 in savings has been achieved by; SONI have reduced their physical assets management and maintenance due to the cloud service provider maintaining the service, eliminating SONI's need to perform hardware updates etc. The SaaS implementations have brought an end expensive upgrade projects IT operational efficiencies - SONI can demonstrate metrics-based service levels; commoditised services can quickly expand and contract with the level of demand SONI employees have greater access to solutions through the cloud SONI have achieved security improvements with modern security offerings from Cloud Service Providers such as Multi Factor Authentication, Conditional Access, Right Management, DLP and MDM SONI's team productivity and focus will have improved through enhanced employee experience: collaboration and productivity tools allowing employees to work more efficiently. SONI will increased their resilience, flexibility and ability to adapt to increasing complexity of demand in their external market place. SONI have refocused away from on-premises technologies (and the resources required to implement and operate) for commoditised IT to areas more directly relevant to the operation of the core business and the organisations strategic objectives' | SONI needs to set out milestones for all elements of their transition to cloud /deliverables In relation to the success factor of SONI increasing resilience, flexibility and ability to adapt to increasing complexity of demand in their external market place. SONI need to be more specific and provide clear examples as to how the cloud transition will help achieve these things. SONI need to provide more detail and clarity as to what is meant by refocussing to 'areas more directly relevant to the operation of the core business and the organisations strategic objectives'. | SONI business plan, D-49 SONI Deep Dive response, P10
Cloud based apps | Transition to cloud-based applications rather than installing on-premises versions (Software as a Service)
Cloud based services | Deployment of new cloud-based services such as advanced analytics (Platform as a Service)
Initiative D3 - IT Operating Model | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or ambition | Reference used for deliverable information
Create a modern and agile service delivery organisation to further efficiency and increase security of our data centres and enable sustainable growth in data capacity | Initial assessment of the existing operating model | [12 empty] | SONI needs to set out milestones for all deliverables within this intiative | SONI Business Plan, D56
| Strategy and design of new model including change management planning | [13 empty] | SONI Business Plan, D56
| Planning of transition project | [13 empty] | SONI Business Plan, D56
| Risk assessment and final approvals | [13 empty] | SONI Business Plan, D56
| Implementation of modern and agile serivice delivery model | [11 empty] | SONI have implemented a modern and agile service delivery model. This model helps ensure resilience of the services to SONI's customers and meet current and future needs of the business. | SONI need to provide more detail as exactly how the resilience of services to customers will be ensured and how this will meet current and future business needs | SONI Business Plan, D56
Data Centre Optimisation | Review data centre strategy | [11 empty] | SONI have successfully reviewed their data centre strategy. This ensures SONI have met the range of security obligations imposed by the NIS Directive. |  | SONI Business Plan, D57
| Data Centre Optimisation | [11 empty] | SONI have outsourced and co-located data centres and have now improved availability, reliability, resilience, flexibility and security (both physical and cyber) as well as reduction in overhead costs, improved service and offer the ability to take advantage of new technology deployment and usage options. Redacted Increased level of efficiency and increase security of data centres and enable sustainable growth in capacity, supporting the anticipated increases in standing data volumes |  | SONI Business Plan, D56, D58
Improved Vendor management and agile project delivery | The adoption of agile principles in service delivery, including anticipating business needs and forecasting resource planning responsively on a monthly basis, testing and adapting projects 'in-flight' if needed and working in close contact with business customer stakeholders. | [11 empty] | SONI have adopted agile principles in service delivery. This in turn has enhanced vendor performance, compliance with contractual obligations and improved commercial outcomes for SONI. |  | SONI Business Plan, D-56
| Increase in specialist staff resources to facilitate this step change in vendor/contract management, from a primarily technical approach to an agile, commercial focus. | [11 empty] | Specialist staff hired who have successfully facilitated these changes |  | SONI Business Plan, D-56
| Encorporate the following change initiaitves; Establish a simple charter for vendor management; Increase visibility into external spending; Collect and catalogue vendor contracts; Publish basic rules of engagement; and Develop performance standards for vendors | [11 empty] | SONI have successfully incorporated all of the change initiatives |  | SONI Business Plan, D59
| Define, agree and implement vendor KPIs that provide measurements based on actual historical performance. These vendor management KPIs can form part of a balanced scorecard covering areas key to the value delivered by the vendor relationship | [11 empty] | SONI have implemented vendor KPIs, have developed measurements and are reporting on these KPIs. SONI have identified vendor performance issues in the measurement areas. These KPI's have helped develop remedies for relationship problems with vendors ISONI use the KPIs to include measures that report the direct and indirect implications of supplier performance on the business |  | SONI Business Plan, D-60
Initiative D4 – Simplify & Standardise IT Solutions | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub intiative | [13 empty] | SONI needs to set out milestones for all deliverables within this intiative
Application Rationalisation | Reduce the number of individual business solutions that are part of SONI’s application landscape | [11 empty] | SONI's business solutions have reduce in overall complexity, SONI's inter-application data integration will become reduced, SONI's efforts to support and maintain a large number of separate applications will decrease SONI will save money due to reduced information technology infrastructure and software license costs. | More specific examples needed here to demonstrate exactly how SONI will achieve these measures of success. | SONI business plan, D-63
Capacity Market Platform | Make small/medium changes to the platform to accommodate changing industry requirements and business and technical platform improvements. | [11 empty] | These small/medium changes to the platform will help ensure that there is sufficient generating capacity to meet our security of supply at the lowest cost. | What are the small/medium changes and how will they help achieve success? | SONI business plan, D-66
Middleware Changes (OSB and GDX) | SONI migrating solutions that use GDX (Group Data eXchange) to OSB (Oracle Service Bus) | [11 empty] | SONI have successfully migrated business solutions that use GDX to OSB. |  | SONI business plan, D-66
Initiative D5 - Maintain Cyber Security | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative | [13 empty] | SONI needs to set out milestones for all deliverables within this intiative
Enterprise Backup Enhancements | Upgrades to SONI’s current On Premise Back Up solution. Continued investigation into moving the Enterprise Backup system to the cloud | [11 empty] | SONI's upgrades have ensured the availability of systems, data and information in the event of loss of equipment or a corruption or other malicious intervention. Cyber security threat (such as malware) are partially mitigated by the backup solutions. SONI data backup policy ensures protection against system failure or data loss (which could be caused by corruption or malicious deletion). If Cloud based backup solutions are proven to work for SONI they would deliver a backup solution which is a full service model - this would reduce/remove the requirement to purchase tapes, disk storage, licences to maintain the backup facility on premises. SONI have met their obligations as set out in NIS18 and the additional guidance provided by the UK's Centre for the Protection of Critical National infrastructure | What will success look like with regards to ongoing investigation in moving the back up systems to the cloud? What are the timelines for this investigation? | SONI business plan, D-69
F5 Enterprise Refresh | BigIP F5 load balancers and gateway devices replacement | [11 empty] | SONI have successfully replaced BigIP F5 load balancers and gateway devices, SONI can continue to distribute load to applications in real time and also reduce outage times should a device or application component fail in one of its corporate applications. |  | SONI business plan, D-69
Firewalls | Replacement of Firewalls | [11 empty] | SONI have successfully replaced this equipment and therefore have maintain support, cater for growing data volumes and to ensure security in the context of an increasingly challenging cyber security landscape.
Email and Web Protection Refresh | Replacement of email and Web Protection Refresh | [11 empty] | The replacement of this equipment will maintain support, cater for growing data volumes and to ensure security in the context of an increasingly challenging cyber security landscape
Intrusion Prevention Systems (IPS) /Intrusion Detection Systems (IDS) Refresh | Replacement of IPS and IDS | [11 empty] | SONI have successfully replaced this equipment will maintain support, cater for growing data volumes and to ensure security in the context of an increasingly challenging cyber security landscape. Newer technology has facilitated central management and improved the use of threat intelligence information. | Newer technology will facilitate central management and improved use of threat intelligence information'.How will new tech facilitate this? More information is needed from SONI here | SONI business plan, D-71
Cyber Security Awareness Training | Ongoing cyber security awareness training to staff | [11 empty] | Staff will continue to be trained and therefore have the necessary cyber awareness and cyber hygiene knowledge |  | SONI business plan, D-71
Initiative D6 –SONI Work Place BAU | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub intiative | [13 empty] | SONI needs to set out milestones for all deliverables within this intiative
Gas Boilers | Gas boilers to be replaced at SONI | [11 empty] | Gas boiler replaced successfully. |  | SONI business plan, D-73
Small Projects | Replace various small projects at Catlereagh house as indicated in the Final Determination | [11 empty] | Small projects replaced successfully. |  | SONI business plan, D-73
Initiative E1 Telecoms Opex and Capex | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative | [13 empty] | SONI needs to set out milestones for all deliverables within this intiative
Capex | Progress with RTU Replacement Project and transfer of assets with NIEN | [11 empty] | Successful engagement and transfer with NIEN. Engagement will be facilitated via an updated and agreed TIA. |  | UR created success measure
| Progress with UPS Replacement Project and transfer of assets with NIEN | [11 empty] | Successful engagement and transfer with NIEN. Engagement will be facilitated via an updated and agreed TIA. |  | UR created success measure
| Moyle HVDC Project | [11 empty] | SONI have successfully completed the project, integrating a new control system into SONI EMS. SONI have replaced the existing analogue system with an IP solution utilising IEC 104. SONI have developed a new set of requirements for the data to be dispatched, displayed and captured in the SONI EMS. |  | SONI business plan, E-15
| Ballylumford 275kv Upgrade | [11 empty] | SONI have successfully supported NIEN's Ballylumford Power Station project with the replacement of a new RTU, |  | SONI business plan, E-15
| IP Telephony Upgrade | [11 empty] | SONI have successfully upgraded and replaced the system in 2025. |  | SONI business plan, E-15
Opex | OFCOM notice of Product Withdrawal – Analogue Voice Services | [11 empty] | SONI is compliant with the system restoration plan and Civil Contingency Plan. SONI can communicate with the relevant government bodies during a significant power outage. |  | SONI business plan, E-13
| Disturbance Monitoring Services- Over the 2020-2025 Price Control period SONI expects to have to pay £250k to have access to the telecommunications circuits for Disturbance Recording | [11 empty] | SONI continue to have access to the telecommunications circuits for Disturbance Recording |  | SONI business plan, E-13
| Operational Telephony and Emergency Voice Over the period 2020 – 2025 SONI expects to pay £1.1m in providing the Emergency Voice Telecommunication Systems through an outsourced Telecommunications Service Provider and through the Police Services Northern Ireland (PSNI) Emergency Voice System. | [11 empty] | SONI have invested the awarded money and the Emergency Voice Telecommunication Systems through an outsourced Telecommunications Service Provider and through the Police Services Northern Ireland (PSNI) Emergency Voice System. |  | SONI business plan, E-13
| NIEN engagement and TIA progress | [11 empty] | Finalised TIA to be submitted and agreed in 2021 |  | UR created success measure
Initiative F1 Renewables Strategy: research, development, implementation opex and TSO/DSO capex interface | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative opex phases & illustrative types of activity relating to opex
Scoping and start up(opex) | SONI seeks to develop a programme to research, develop, innovate and test the robustness of new policies, processes and tools which will allow integration of high levels of RES into the electricity system in a safe and secure manner. Scoping - It will need to define objectives and scope of the project ; Constraints and assumptions stated; Estimated costs and benefits; Lessons learned/research, engagement etc. Start up - Project initiation document / Modelled costs / benefits / Investment proposal for requirements and design / Allocated resources etc. | [11 empty] | SONI to provide comprehensive, joined-up, well-evidenced and justified and clear proposal to UR detailing the findins of its scoping and start phase actvity, which has been tested effectively with diverse set of stakeholders. | Clear deliverable definition and specification, milestones, success measures set out within proposal. SONI is also likely to need to take account of variety of UR service priorities (see FD chapter 2: UR strategic priorities for SONI performance: all seem relevant with exception of other priorities) SONI may also want to ensure consistency and readacross from digitalisation and whole sytem strategy development initiatives, and outputs of certain aspects of stakeholder engagement activity (e.g. H7 allowance) | SONI business plan, F-13, SONI Annex I of DD response, and UR view
Requirements and design phase (opex) | Defined Functional design and solution, Development and implementation plan and budget, Support and transition plan
Development and testing (opex) | developed solution/ testing complete etc.
Implementation | Solution/service implemented in production; Post implementation support concluded and handover complete; Post investment appraisal plan complete etc.
Renewables Strategy (TSO- DSO interface Capex) | Develop interfaces between the TSO and DSOs that enable the sharing of data and coordination in decision making | [12 empty] | Clear deliverable definition and specification, milestones, success measures set out within proposal. SONI may also seek to take account of variety of UR service priorities (see FD chapter 2: UR strategic priorities for SONI performance: all seem relevant with exception of 'other priorities') SONI may also want to ensure consistency and readacross from digitalisation and whole sytem strategy development initiatives We expect SONI to engage effectively with NI DSO. We consider that the NI DSO should lead on this development rather than SONI. | SONI business plan, F-15, SONI annex I of DD response
Initiative F2 Control Centre Tools opex | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative opex phases & types of opex actvity
Scoping and start up | SONI requires a programme to develop new control room tools which will allow integration of high levels of RES into the electricity system in a safe and secure manner. Scoping - SONI will need to define objectives and scope of the project ; Constraints and assumptions stated; Estimated costs and benefits; Lessons learned/research, engagement etc. Start up - Project initiation document / Modelled costs / benefits / Investment proposal for requirements and design / Allocated resources etc. | [11 empty] | SONI to provide comprehensive, joined-up, well-evidenced and justified and clear proposal to UR detailing the findings from its scoping and start phase actvity, which has been tested effectively with diverse set of stakeholders. | Clear deliverable definition and specification, milestones, success measures set out within proposal. SONI is also likely to need to take account of variety of UR service priorities (see FD chapter 2: UR strategic priorities for SONI performance: all seem relevant with exception of 'other priorities') SONI may also want to ensure consistency and readacross from digitalisation and whole sytem strategy development initiatives, and outputs of certain aspects of stakeholder engagement activity (e.g. H7 allowance) | SONI business plan, F-20 and UR view
Requirements and design phase (opex) | Defined Functional design and solution, Development and implementation plan and budget, Support and transition plan
Development and testing (opex) | developed solution/ testing complete etc.
Implementation (opex) | Solution/service implemented in production; Post implementation support concluded and handover complete; Post investment appraisal plan complete etc. | [13 empty] | UR created success measure
Initiative F3 Smarter Outage Management | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative | [13 empty] | SONI needs to set out milestones for all deliverables within this intiative. Final success measures would also benefit from further clarity and specification and need final delivery dates
| Stage 1: Analysis and solution specification. | [11 empty] | Document existing outage management processes and identify desired target processes including interface requirements. This will be used to create a tender specification document. |  | SONI business plan, F-36
| Stage 2: Procurement and supplier selection. | [11 empty] | Engage the market and publish the tender specification. Following evaluation of tender responses, select the supplier providing the best overall value. |  | SONI business plan, F-36
| Stage 3: Solution implementation and validation. | [11 empty] | Work with preferred supplier to implement and validate a new OMS by 2021-22. |  | SONI business plan, F-36
| Stage 4: System support. | [11 empty] | Work with preferred supplier to provide intensive post-deployment support to facilitate a smooth transition. |  | SONI business plan, F-36
| Outage management governance framework. | [11 empty] | Delivery of outage management governance framework with agreement of TSOs & DSOs & third parties. |  | SONI business plan, F-38
| Increased visibility of outages | [11 empty] | Monitor visibility of outages at distribution level which could impact on system services provision. |  | SONI business plan, F-38
| Monitor impact of outages on DBC's | [11 empty] | Smarter outage management will allow SONI to assess the impact of transmission outages on the dispatch balancing cost element of that charge. |  | SONI business plan, F-32
Initiative F6 System Planning | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative | [13 empty] | SONI needs to set out clarify and specifiy what is being delivered (e.g. what is being reviewed on ongoing basis) milestones for all deliverables within this intiative. Final success measures would also benefit from further clarity and specification and need final delivery dates
| Ongoing review of the needs of the Transmission System with reference to ongoing market requirements, SONI's licence conditions as well as the nature of the renewables and technologies expected in the price control. | [11 empty] | Timely completion of TDPNI, generator and transmission capacity statements in line with licence requirements. |  | SONI business plan, F-51
| Update and enhance SONI's appraisal processes. In particular reviewing those that require dynamic analysis (e.g. transient/frequency/voltage stability, harmonics, temporary overvoltage, transitory recovery, switching studies). | [11 empty] | Efficient, timely and quality submissions of TNPP's to progress network solutions. |  | SONI business plan, F-51
Initiative F8 Clean Energy Package | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or ambition | Reference used for deliverable information
Sub Initiative | [12 empty] | Capex has been awarded to SONI which which will be used to allow for the cost for professional fees for high-level design analysis to implement the CEP. Once these exploratory works have been complete, this will provide SONI with the information needed to come back with a proposals for the clean energy package under our uncertainty mechanisms. | SONI will need clarify and specifiy what is being delivered (e.g. what is being reviewed on ongoing basis) milestones for all deliverables within this intiative. Final success measures would also benefit from further clarity and specification and need final delivery dates
Provisions for regional cooperation (RCCs)
European resource adequacy assessment
Bidding Zone methodologies, review & reporting on structural congestions
Capacity mechanisms’ registry and provisions for foreign capacity participation
Risk preparedness framework and methodologies
TSO-DSO cooperation on new tasks through the future EU DSO entity, future Network Codes’ drafting process, legal implications and penalties
Initiative G4 – Cyber Security Enhancements | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative | Redacted | [11 empty] | Redacted | SONI needs to set out milestones for all deliverables within this intiative How will this enhance SONI's resilience posture to current and emerging threats? | SONI business plan, G30, G31
| Redacted | [11 empty] | Redacted | More detail needed on what does good practice looks like for this framework? | SONI business plan, G30, G31
| Redacted | [11 empty] | Redacted | What steps will be taken to increase focus and investment in security awareness and threat intelligence? | SONI business plan, G30, G31
| Redacted | [11 empty] | Redacted | Timelines for the security operations centre to be completec. More specifics on which processes and technology for the security operations centre needed. | SONI business plan, G30, G31 SONI deep dive response, p27
| Redacted | [11 empty] | Redacted. | How/what methods will SONI use to increase oversight and reporting on threat and risk management? More details needed. | SONI business plan, G30, G31
| Redacted | [11 empty] | Redacted | How will these capabilities be enhanced? | SONI business plan, G30, G31
Risk mitigation and performance improvement controls | Redacted | [11 empty] | Redacted |  | SONI business plan, G31
| Redacted | [11 empty] | Redacted |  | SONI business plan, G31
| Redacted | [11 empty] | Redacted |  | SONI business plan, G31
| Redacted | [11 empty] | Redacted |  | SONI business plan, G31
Initiative G5 – European Network Codes | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/orUR service priorities | Reference used for deliverable information
Sub Initiative | [13 empty] | SONI needs to set out milestones for all deliverables within this intiative. SONI will need to further clarify and specifiy what is being delivered milestones for all deliverables within this intiative. Final success measures would also benefit from further clarity and specification and need final delivery dates
| Continuously work with regulators, governments and key stakeholders to resolve issues with the code parameters | [11 empty] | Continuous work with regulators, governments and key stakeholders has ensured any issues with code parameters have been resolved. |  | SONI business plan, G36
| Regularly review and update the codes to ensure they are fit for purpose as technology and system requirements develop | [11 empty] | Codes are fit for purpose as they are regularly reviewed and updated |  | SONI business plan, G36
| Develop additional European Network Codes over the next price control period to cover technologies / issues not addressed at present (e.g. storage); | [11 empty] | SONI have developed additional network codes which have addressed issues that have not been dealt with at the beginning of the Price Control period (2020) |  | SONI business plan, G36
| Update the Northern Ireland Grid Codes to reflect changes or new European Network Code requirements | [11 empty] | Grid code updated accurately and reflects changes or new EU network codes |  | SONI business plan, G36
| Ensure compliance across the entirety of the codes to make sure SONI’s legal obligations are met | [11 empty] | SONI have continued to meet their EU network code legal obligations as they have remained compliant across all codes. |  | SONI business plan, G36
| Submit information, as necessary, to ENTSO-E as part of ENTSO-E’s monitoring role. | [11 empty] | Submissions to ENTSO-E are accurate and on time |  | SONI business plan, G36
Initiative G6 - Capacity Market Secondary Trading | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative
| Manage the manual secondary trading that is being implemented as an interim solution | [11 empty] | Ongoing manual management throughout Y1 and Y2. |  | UR created success measure
| Monitor the level of secondary trading activity using the manual process and the capacity traded. | [11 empty] | Clear record and report on the number of trades and volume of capacity traded throughout Y1 and Y2. |  | SONI business plan, G-44
| Provide an update report to UR on trading levels and performance of the interim solution after 2 years of operation. | [11 empty] | Provide a clear report to UR at end of Y2 with relevant statistics and evaluation of manual trading platform. |  | UR created success measure
| Monitor forced outages and improved overall availability in the Capacity Market through availability statistics. | [11 empty] | Record and report on forced outages and availability throughout Y1 and Y2. |  | SONI business plan, G-44
Initiative G7 - DSU state aid compliance | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative
| Undertake metering of DSUs not currently subject to measurement. | [11 empty] | Calculation of Metered Quantities for DSUs over 1GW of generation. |  | SONI business plan, G-47
| Record/report on the number of DSUs monitored. | [11 empty] | Record and report on number of DSU monitored. |  | SONI business plan, G-48
| Record/report on the capacity of DSUs not subject to metering post project implementation. | [11 empty] | Record and report on number and capaity of DSUs not subject to metering. |  | UR created success measure
Initiative H7 - Transforming customer engagment: "Year 1 understanding" & "website improvements" and engagement platform" | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on further accountability and/orUR service priorities | Reference used for deliverable information
Sub Initiative | [13 empty] | SONI needs to set out milestones for all deliverables within this intiative. SONI will need to further clarify and specifiy what is being delivered. Final success measures would also benefit from further clarity and specification and need final delivery dates
Understanding | "Year 1 - understanding - Undertake research to develop understanding of stakeholder segments and needs" | [11 empty] | Comprehensive and well considered report to be provided as part of August 2021 performance report on stakeholder needs assessment. | SONI is also likely to need to take account of variety of UR service priorities (see FD chapter 2: UR strategic priorities for SONI performance: all seem relevant with exception of 'other priorities') SONI may also want to ensure consistency and readacross from digitalisation and whole sytem strategy development initiatives, and further development of its key strategic initatives relating to renewables strategy and control centre tools | SONI DD consultation response, C-14 and UR view
| " Year 1 - understanding - Desktop study to identify which engagement opportunities are utilised by other comparators (e.g. NG ESO) and which will be most beneficial to Northern Ireland" | [11 empty] | Comprehensive and well considered report to be provided provided as part of August 2021 performance report on engagement bechmarking. | SONI is also likely to need to take account of variety of UR service priorities (see FD chapter 2: UR strategic priorities for SONI performance: all seem relevant with exception of 'other priorities') SONI may also want to ensure consistency and readacross from digitalisation and whole sytem strategy development initiatives, and further development of its key strategic initatives relating to renewables strategy and control centre tools | SONI DD consultation response, C-14 and UR view
| "Year 1 - understanding SONI Enhanced Customer and Stakeholder Engagement Strategy " | [11 empty] | Clear and holistic strategy to be published by 2021-22. | SONI is also likely to need to take account of variety of UR service priorities (see FD chapter 2: UR strategic priorities for SONI performance: all seem relevant with exception of 'other priorities') SONI may also want to ensure consistency and readacross from digitalisation and whole sytem strategy development initiatives, and further development of its key strategic initatives relating to renewables strategy and control centre tools | SONI DD consultation response, C-14
| " Year 1 - understanding - Identify specific areas for research / projects based on segmentation and desktop studies " | [11 empty] | Identify specific areas for research / projects based on segmentation and desktop studies. | SONI is also likely to need to take account of variety of UR service priorities (see FD chapter 2: UR strategic priorities for SONI performance: all seem relevant with exception of 'other priorities') SONI may also want to ensure consistency and readacross from digitalisation and whole sytem strategy development initiatives, and further development of its key strategic initatives relating to renewables strategy and control centre tools | SONI DD consultation response, C-14
Website improvements | New SONI website | [11 empty] | A new SONI website to be delivered by 2021-22, including a new platform which allows a portal for communications to all business, technical and non-industry audiences. |  | SONI DD consultation response, C-12
Engagement Platform | New SONI online engagement platform | [11 empty] | A new stakeholder engagement online forum to be completed by 2021-22 in order to facilitate specific discussion across our stakeholder segments. |  | SONI DD consultation response, C-12

## Non-Hypothecaated Funding
Initiative H3 - Pre-Application Process | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative
| Develop and provide a pre-application process for connections to put in place; - formal agreements, - clear processes - service level agreements. | [11 empty] | Develop pre-connection SLA's and monitor / report against performance. |  | SONI business plan, H-18
| Publish up to date information on network capacity and generation | [11 empty] | Provide customers with up to date information on a monthly basis, addressing their feedback for this service, provide consistency and transparency for customers. |  | SONI business plan, H-19
Initiative H6 - Dedicated Customer Account Team | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | UR Comments on develop further accountability and/or UR service priorities | Reference used for deliverable information
Sub Initiative
| Introduce and formalise a dedicated customer account team with a single account manager. | [11 empty] | Customer Account Management function in place for 2021. |  | SONI business plan, H-32
| Develop an engagement strategy for each customer type. | [11 empty] | Develop an engagement strategy for each customer type. |  | SONI business plan, H-31

## Grid security scoping start up
1. Initiaitve / Sub Intiative: As demonstrated in the current table below please state the intiative/sub initiative the deliverable is linked to.
2. Deliverable: Please outline in detail what is being delivered being specific about what it is that you will be doing to achieve the goal.
3. Related IT Investment: If a deliverable is linked to an IT Investment please list what investments and explain how it links to the deliverable.
4. Year Milestones: Please outline the key milestones you expect to reach in the respective year. These should be detailed and clear enough that it will be
obvious whether or not these milestones were met. There should be at least one milestone in each year unless the project is not expected to be started
at this point. Where this is the case please state it. Please try to avoid making dates open ended.
5.Year Success: Please detail what success would look like for each deliverable in each given year. This should be detailed and clear enough that it will be
obvious whether or not these milestones were met. – Not necessarily the specifications of what will be delivered but what will be achieved.
6. Expected final delivery date and what success looks like: Please outline when the final project will be delivered and explain what success looks like for
the final delivery of the deliverable.
Preliminary Scoping Assessment: Alternative Site for a Disaster Recovery, Business Continuity site in Northern Ireland (relating to Initiative G.1) | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | Reference used for deliverable information
| redacted. |  | redacted. | n/a | [8 empty] | Redacted
Scoping and start up: Physical Security Technology Replacement and Enhancement (relating to Initiative G:3) | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | Reference used for deliverable information
| redacted |  | redacted | [9 empty] | redacted

## UR service expectations
1. Initiaitve / Sub Intiative: As demonstrated in the current table below please state the intiative/sub initiative the deliverable is linked to.
2. Deliverable: Please outline in detail what is being delivered being specific about what it is that you will be doing to achieve the goal.
3. Related IT Investment: If a deliverable is linked to an IT Investment please list what investments and explain how it links to the deliverable.
4. Year Milestones: Please outline the key milestones you expect to reach in the respective year. These should be detailed and clear enough that it will be
obvious whether or not these milestones were met. There should be at least one milestone in each year unless the project is not expected to be started
at this point. Where this is the case please state it. Please try to avoid making dates open ended.
5.Year Success: Please detail what success would look like for each deliverable in each given year. This should be detailed and clear enough that it will be
obvious whether or not these milestones were met. – Not necessarily the specifications of what will be delivered but what will be achieved.
6. Expected final delivery date and what success looks like: Please outline when the final project will be delivered and explain what success looks like for
the final delivery of the deliverable.
UR service expectations: Digitilisation Strategy | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | Reference used for deliverable information
Sub Initiative
Strategic vision and ambition | Strategy on what Digitilisation role SONI seeks to play across all TSO SONI roles and services and and how this will benefit NI customers, stakeholders and consumers in terms of outcomes |  |  | Provided as part of August 2021 performance plan |  |  |  | Ambitious for consumer, comprehensive and clear findings in line with diverse set of stakeholder needs and UR service expectation
Innovative best practice/lessons learned | Assessment of digitilisation best practice innovation and lessons learned elsewhere and what may work in an NI context |  |  | Provided as part of August 2021 performance plan |  |  |  | Ambitious for consumer , comprehensive and clear findings based on lessons elsewhere, along with clear analysis of what may work in NI, along with appropriate justification
User needs and engagement | Assessment of SONI user needs, strategy to engage and collaborate users, and clear resulting actions |  |  | Provided as part of August 2021 performance plan |  |  |  | Ambitious for consumer , comprehensive and clear findings in line with diverse set of stakeholder and UR service expectation
People planning | Strategy for how SONI is going to ensure that its workforce has the right capabilities, culture and how it will embed ideas and learning into the organisation, across digital, data and technology areas |  |  | Provided as part of August 2021 performance plan |  |  |  | clear strategy for how SONI is going to ensure that its workforce has the right capabilities, culture and how it will embed ideas and learning into the organisation, across digital, data and technology areas, across its TSO role areas
Governance | Strategy for SONI ownership of governance, corporate interactions and accountability to promote and account for a culture of digitilisation |  |  | Provided as part of August 2021 performance plan |  |  |  | clear and meaningul strategy for SONI ownership of governance, corporate interactions and accountability to promote and account for a culture of digitilisation
Coordination and engagement | Strategy for engaging and collaborating with stakeholders, customers and taking account of consumer interests. |  |  | Provided as part of August 2021 performance plan |  |  |  | Holistic and comprehensive strategy for engaging and collaborating with stakeholders, customers and taking account of consumer interests.
Actions and delivery | Action and delivery plan to meet users’ needs across the services that SONI offers, to include cost, benefit, options, prioritisation, delivery/timing. Milestones, success measures, deliverables |  |  | Provided as part of August 2021 performance plan |  |  |  | comprehensive and clear action and delivery plan
UR service expectations: whole system thinking strategy | Deliverable | Related IT investment | 2020/21 milestones | 2021/22 milestones | 2022/23 milestones | 2023/24 milestones | 2024/25 milestones | Year 1 success | Year 2 success | Year 3 success | Year 4 success | Year 5 success | Expected final delivery date and what success looks like | Reference used for deliverable information
Sub Initiative
Strategic vision and ambition | Overarching strategic ambition across all TSO SONI roles and services and how this is going to benefit NI customers, stakeholders and consumers in terms of outcomes |  |  | Provided as part of August 2021 performance plan |  |  |  | Ambitious for consumer, comprehensive and clear findings, accounting for a diverse set of stakeholder needs and UR service expectation
Roles and responsibilities | Description and justification across all SONI roles and services for how SONI views its: - roles and responsbilities for interfacing with NIE Networks across the transmission and distribution interface, acoss its role as DNO, DSO, TAO. Roles and responsibilities should be developed and agreed with NIE Networks, and stakeholders and customers should be engaged with. - role and responsibilities for coordinating across the wider electricity system (beyond the distribution and transmission interface) and also on a cross-vector basis |  |  | Provided as part of August 2021 performance plan |  |  |  | Clear and coordinated thinking on roles and responsibilites based on engagement with 3rd parties, including DSO.
Innovative best practice/lessons learned | Assessment of best practice innovation and lessons learned elsewhere that could be relevant to SONI whole system thinking; and what may work in an NI context |  |  | Provided as part of August 2021 performance plan |  |  |  | Ambitious for consumer , comprehensive and clear findings based on lessons elsewhere, along with clear analysis of what may work in NI, along with appropriate justification
People planning | Strategy setting out how SONI is going to ensure that its workforce will have the right capabilities, culture and how it will embed ideas into SONI organisation |  |  | Provided as part of August 2021 performance plan |  |  |  | clear strategy for how SONI is going to ensure that its workforce has the right capabilities, culture and how it will embed ideas and learning into the organisation, across digital, data and technology areas, across its TSO role areas.
Governance | Plan and processes for organisational governance, corporate interactions and accountability to promote and account for a culture of whole system thinking |  |  | Provided as part of August 2021 performance plan |  |  |  | clear and meaningul strategy for SONI ownership of governance, corporate interactions and accountability to promote whole system thinking
Coordination and engagement | Plan and process for engaging and collaborating with stakeholders, customers, and taking account of consumer interests, across all SONI roles and services |  |  | Provided as part of August 2021 performance plan |  |  |  | Holistic, clear and comprehensive strategy for engaging and collaborating with stakeholders, customers and taking account of consumer interests.
Actions and delivery | Action and delivery plan to meet partner, stakeholder, customer and consumer interests, across the services that SONI offers, to include cost, benefit, options, prioritisation, and delivery/timing. Milestones, success measures, deliverables. |  |  | Provided as part of August 2021 performance plan |  |  |  | comprehensive and clear action and delivery plan